## Checklist
#VALUE!
Launch Assurance Checklist | Responsible Party | Due Date | Completed | Notes
Gather and validate product information relevant for CMS and Price Transparency requirements and validate it against the FDA product database. |  | 120 days prior to launch
Conduct price modeling to determine WAC impact for Price Transparency Reporting requirements and Government Pricing Calculation price modeling. |  | 90 - 120 days prior to launch
Load product information to Government Pricing and Price Transparency Reporting solutions. Load WAC and calculate the estimated PHS price. |  | 90 days prior to launch
Report on new products for triggered states that require Price Transaprency Reporting. |  | Variable, 60 days prior to launch
Load new products to MDP , following launch. |  | Post launch
Load new products to the ASP portal quarterly. |  | Post launch
Load new products to HRSA OPAIS quarterly. |  | Post launch
Product Certification in MDP, HRSA, and ASP Portal. |  | Prior to the 30th each month
Send new product and contract pricing to 3PL for distribution. |  | Dependant on 3PL agreement
Following first full quarterly Government Pricing calculation conduct PHS price adjustment, load revised pricing with customers and in RMS, and if necessary, issue credit and rebills of historic PHS transactions. |  | Within 30 days, post launch